## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | Estbalish User Stories | 1 | High | Done | 1
2 | Prepare Kanban | 1 | High | Done | 2
3 | Estbalish functional and nonfunctionl requirements | 1 | High | Done | 2
4 | Prepare code for opening page | 1 | High | Done | 3
5 | Wireframes | 1 | High | Done | 3
6 | As a user, I want to learn about the sustainability of AI, so I can know how much to limit my reliance. | 2 | Medium | To Do | 2
7 | As a user, I want to understand how AI works, so I can better gauge the accuracy of claims about AI. | 2 | Medium | To Do | 2
8 | As a user, I want a clear overview of the benefits of AI literacy when I first open the app, so that I understand why investing my time in learning about AI is valuable. | 2 | High | To Do | 3
9 | As a user, I want to learn about the weaknesses of AI so I can avoid using it in those situations. | 2 | Medium | To Do | 2
10 | As a user, I want to visualize how AI “thinks” so that I can better understand what is going on when I submit a prompt. | 2 | High | To Do | 3
11 | As a user, I want to understand the legal implications of using these tools to ensure I am complying with legal standards and recommendations. | 3 | Medium | To Do | 2
12 | As a user, I want to be more informed about the ethical considerations, so I can use the tool responsibly and in an informed manner. | 3 | Low | To Do | 2
13 | As a user, I want instructions on how to design effective prompts, so that I can use AI tools more effectively and get better results. | 3 | High | To Do | 3
14 | As a user, I want to explore real-world examples of AI applications to see how AI is utilized across various industries. | 3 | High | To Do | 2
15 | As a user, I want to compare traditional problem-solving methods with AI-driven ones so that I can understand AI’s unique advantages and potential downsides. | 3 | Low | To Do | 3
16 | As a user, I want interactive activities that let me experiment with AI tools so that I can learn through hands-on experience. | 3 or 4 | High | To Do | 3
17 | As a user, I want to discover how AI affects privacy and data security so that I can make informed choices about sharing information. | 4 | Low | To Do | 3
18 | As a user, I want to learn how bias in training data affects what I see when I use AI, so that I can be cognizant of whether or not AI generated content is reinforcing my own biases. | 4 | Medium | To Do | 3
19 | As a user, I want to learn what happens to my ownership over my materials that I upload to an AI generator once I hit “generate”, so that I can make informed choices about what I upload. | 4 | Low | To Do | 2
20 | As a user, I want a learning experience that can load even when I’m in an area with bad internet so that my learning isn’t hindered by unnecessary frustration. | 5 | Low | To Do | 3
21 | As a user, I want to see cited sources, so I can verify and trust what I've learned. | 5 | High | To Do | 2
22 | As a user, I want learning materials to be as concise as possible, so that I’m not wasting time I could be using to do other things. | 5 | Medium | To Do | 2
23 | As a user, I want to have real-time feedback on my checks for understanding, so that I can alter my approach as I go. | 5 | High | To Do | 3

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657