## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
1 | Estbalish User Stories | Edit stories for final list using feedback | 1 | Completeing and finalizing user stories. Editing user stories using feedback. | NF-KA | 1 | 1 | P1 25, P2 25, P3 25, P4 25
2 | Prepare Kanban | Create kanban for Team B and assign all issues under todo/sprint | 1 | Create Kanban for team B and add all issues for deliverable one and understand the functions of Kanban | NF-T | 2 | 2 | P1 50, P2 50, P3 0, P4 0
3 | Estbalish functional and nonfunctionl requirements | Produce list of features | 1 | UI design | F | 3 | 3 | P1 25, P2 25, P3 25, P4 25
4 | Prepare code for opening page | Preapre the main UI | 1 | Main UI design | F | 3 | 3 | P1 25, P2 25, P3 25, P4 25
5 | Wireframes | Design inital mockups | 1 | Design inital mockups | F | 3 | 3 | P1 0, P2 100, P3 0, P4
6 | As a user, I want to learn about the sustainability of AI, so I can know how much to limit my reliance. | Research sustainability of AI and create educational content | 2 | Develop initial educational content for AI literacy app | F | 2 | 0
7 | As a user, I want to understand how AI works, so I can better gauge the accuracy of claims about AI. | Create visual explainer on AI functioning | 2 | Develop initial educational content for AI literacy app | F | 2 | 0
8 | As a user, I want a clear overview of the benefits of AI literacy when I first open the app, so that I understand why investing my time in learning about AI is valuable. | Design onboarding and intro screen content | 2 | Create onboarding experience that motivates learning | F | 3 | 0
9 | As a user, I want to learn about the weaknesses of AI so I can avoid using it in those situations. | Develop module explaining AI limitations | 2 | Expand learning modules on responsible AI use | F | 2 | 0
10 | As a user, I want to visualize how AI “thinks” so that I can better understand what is going on when I submit a prompt. | Create an interactive visualization for AI processes | 2 | Make AI concepts more interactive and tangible | F | 3 | 0
11 | As a user, I want to understand the legal implications of using these tools to ensure I am complying with legal standards and recommendations. | Summarize legal frameworks and create a compliance guide | 3 | Address legal and ethical aspects of AI use | NF-KA | 2 | 0
12 | As a user, I want to be more informed about the ethical considerations, so I can use the tool responsibly and in an informed manner. | Build module on ethical AI and responsible use | 3 | Address legal and ethical aspects of AI use | NF-KA | 2 | 0
13 | As a user, I want instructions on how to design effective prompts, so that I can use AI tools more effectively and get better results. | Create tutorial on effective prompting | 3 | Improve user skill and engagement with AI | F | 3 | 0
14 | As a user, I want to explore real-world examples of AI applications to see how AI is utilized across various industries. | Research and build example gallery | 3 | Improve user skill and engagement with AI | F | 2 | 0
15 | As a user, I want to compare traditional problem-solving methods with AI-driven ones so that I can understand AI’s unique advantages and potential downsides. | Develop comparison case study feature | 3 | Deepen understanding of AI’s real-world context | F | 3 | 0
16 | As a user, I want interactive activities that let me experiment with AI tools so that I can learn through hands-on experience. | Build simple AI sandbox for learning | 3 or 4 | Deepen understanding of AI’s real-world context | F | 3 | 0
17 | As a user, I want to discover how AI affects privacy and data security so that I can make informed choices about sharing information. | Develop privacy and data protection learning section | 4 | Expand awareness of data ethics and safety | NF-KA | 3 | 0
18 | As a user, I want to learn how bias in training data affects what I see when I use AI, so that I can be cognizant of whether or not AI generated content is reinforcing my own biases. | Create interactive bias demonstration | 4 | Expand awareness of data ethics and safety | F | 3 | 0
19 | As a user, I want to learn what happens to my ownership over my materials that I upload to an AI generator once I hit “generate”, so that I can make informed choices about what I upload. | Create module on intellectual property and AI | 4 | Deepen understanding of user rights and content ownership | NF-KA | 2 | 0
20 | As a user, I want a learning experience that can load even when I’m in an area with bad internet so that my learning isn’t hindered by unnecessary frustration. | Optimize app for offline functionality | 5 | Improve accessibility and usability | NF-T | 3 | 0
21 | As a user, I want to see cited sources, so I can verify and trust what I've learned. | Add source citation system | 5 | Increase content credibility and user trust | F | 2 | 0
22 | As a user, I want learning materials to be as concise as possible, so that I’m not wasting time I could be using to do other things. | Review and condense educational modules | 5 | Increase content credibility and user trust | NF-KA | 2 | 0
23 | As a user, I want to have real-time feedback on my checks for understanding, so that I can alter my approach as I go. | Build quiz and feedback system | 5 | Add feedback-driven learning experiences | F | 3 | 0

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657